## Project Tracker
TelevEyes Sprint Backlog
Tasks | Assigned To | Status | Estimated Start | Estimated Finish | Estimated Work (in hours) | Notes
Design & Build 'show' database | Josh |  | 2016-09-28 | 2016-10-14
Design User Interface | Khalique & Nathan |  | 2016-09-28 | 2016-10-14 | 16
Code User Interface | TeeTreeo & Billie |  | 2016-09-28 | 2016-10-14 | 20
Bring User Interface together | All |  | 2016-09-28 | 2016-10-14